MTT8 Interim report – Latvia (April through September 2010)

The beginning of the project is April 1, 2010 (project duration April 1, 2010 - March 31, 2011)

| Planned activities | Outcomes of your activities (Please indicate only activities you conducted) Explanations and clarifications please see at fact sheet table attached | Challenges faced during implementation |
| --- | --- | --- |
| A. Awareness raising among policy makers on generic medicines 1. NGO's working group created for a single political point of view on the development of HIV treatment access and expansion of generic drug applications, summarizing national practices in the European Union 2. NGO's working group meeting and the work plan approved 3. MTT8 Report consideration during a meeting of the National HIV coordination commission, discussions animation and acceptance protocol 4. Joint press release of the Commission meeting results by society Association HIV.LV and other NGOs members of the Commission 5. The question of the introduction of generic ARVs in Latvia inclusion into the agenda of the Commission of Social and Employment Issues at the National Parliament 6. Working group representatives participate in plenary of the Commission of Social and Employment Issues at the National Parliament | - April 5, 1-st NGO-s working group meeting: Representatives from NGO-s Association HIV.LV, AGIHAS, DIA+LOGS : Introduction into the MTT8 Report and Advocacy campaign plan - April 7, Logon to meet deputy of the State secretary of the MoH. April 15, Society AGIHAS meets the deputy of the State secretary of the MoH Mr. J. Bundulis - May 13, Conversation with Prime minister Mr. Dombrovskis - July 1, Meeting with Minister of Health Mr. D. Gavars - September 27, Working meeting with the Deputy State Secretary of the Ministry of health Mr. J. Bundulis - May 14, Press conference. Press release published http://www.apvienibahiv.lv/index.php?p=8096&lang=886&a=2&b=1&lbu=3926 - May 28, Meeting with AGIHAS Board Chairman - June 16, NGO-s working group meeting - April 22, The Latvia's chapter of MTT8 Report translated into Latvian - April 25, Press release for Latvia's media presenting the MTT8 report on Latvia and the Global MTT8 Report http://www.apvienibahiv.lv/docs/729/2010-dazhadi/Preses_relize_HIV_LV_260410.pdf April 26, Report in Latvian sent to all stakeholders via e-mail - May 19, MTT8 Latvia's chapter and recommendations presented to theNational HIV Coordination Commission by authors (M. Trapencieris and A. Molokovskis) - Presentations published http://www.apvienibahiv.lv/docs/729/projekti_2010/Prezentacijas_KK_19052010.zip - The minutes published http://www.apvienibahiv.lv/docs/729/Komisiju_protokoli/protokols_19_05_10.doc - June 14, New State Public Health coordination Commission established by MoH. July 7, The 1-st sitting, minutes http://www.apvienibahiv.lv/docs/729/Komisiju_protokoli/Protokols%2007_07_10.doc August 31, The 2-st sitting minutes http://www.apvienibahiv.lv/docs/729/Komisiju_protokoli/Protokols_31_08_10.doc - August 9, The brochure with MTT8 Report Latvia's chapter and shadow UNGASS Report - both in Latvian,- is printed http://www.apvienibahiv.lv/docs/729/projekti_2010/Reports_2010_brochure.pdf - August 31, Proposals to the National Public Health Strategy for 2011 - 2015 on health services and their availability in prisons submitted http://www.apvienibahiv.lv/index.php?p=8096&lang=886&a=2&b=1&lbu=6678 - May 20, The series of publications, also on MTT8 Report (big interview with author of the Report M. Trapencieris including) http://www.dialogi.lv/article_new.php?id=2968 , http://www.dialogi.lv/article_new.php?id=2969 - May 5, Logon to the sitting of the Comission. - May 10, Invitation received - May 17, Participating and speech in the sitting of the Comission. Members of the Comission are informed on MTT8 Report and its conclusions. Materials distributed within members - October 5, Parlamentary Panel on Public Health of the Commission of Social and Employment Issues sitting. HIV and AIDS in prisons: the prevention and treatment, needs in harm reduction in prisons | It is very clear for all members of the working group that there is no possible to get generic ARV-s at hand during one calendar year in the State a member of the European Union, but it is possible to make some steps towards this goal (for example to reduce data exclusivity from 11 years lowest). Also there is all possibilities to work on reducing ARV-s' prices using another mechanisms. The sitting was very "stormy". MoH representatives were disagree with conclusions and recommendations. They wrote into protocol, that we "must make corrections in the Report". Members of the Parliament are very willing to speak about high prices of medicines and common purchases of medicines by Baltic States, but they are not ready to hear and to speak about generics medicines to treat HIV/AIDS. |
| B. Working group on generic ARVs looking at legal and financial issues in place 1. Working group members meeting with representatives of manufacturers of generic drugs 2. Expanded working group on generic ARVs created, including representatives from MoH, Ministry of Economics, Association towards patent-free medicines, pharmaceutical companies etc. 3. Joint press release on the Expanded working group creating and its expected activity by society Association HIV.LV and other NGOs 4. Extended working group meeting, activities scheduling, delegation of tasks, timetable development 5. Non-governmental organizations follow the developments and monitor them 6. Expanded working group meetings, at least two times 7. Progress Report compilation and publication | - September 28, Working meeting with the Latvian Generic Medicines Association. Latvian "Grindeks AS" is a member of this association, and in the year 2006 had acquired a patent "Nucleoside reverse transcriptase inhibitor combination with Mildronate in HIV/AIDS therapy." - August 11, NGO-s work of Public Function Assessment Panel in Public health issues started. The presentation of the State secretary Mr. R. Mucins of the Ministry of Health is heard - August 25, Public Function Assessment Panel's in Public health recommendations agreed, see pages 12 and 13 at http://www.mk.gov.lv/file/files/aktuali/info_presei/2010/20100908_rvg_fa_prezentacija.pdf - September 8, The statement of Public Function Assessment Panel official announcement's day. Report on Health sphere pages 15 and 16 http://www.mk.gov.lv/file/files/aktuali/info_presei/2010/20100908_rvg_fa_zinojums.pdf | Public Function Assessment Panel was established under the State Chancellery authority. NGO-s were asked to participate in this Panel's work as experts in their respective field. All ministries (MoH including) are angry with Panel's conclusions naming them as non-professional and incompetent. The State Chancellery defended the Panel, also civil society's organisations, against attacks. |
| C. Final report on generic ARVs from the working group in place 1. Draft of final report on generic ARVs from the working group written 2. Discussion on the draft in working group and report finalization 3. Announcement of final report at Press Conference |  |  |
| D. Development of implementation plan 1. Working group meeting to develope implementation plan, activity scheduling, delegation of tasks, timetable development |  |  |
| E. Changes to the legislation proposed to the Parliament 1. The question of the introduction of generic ARVs in Latvia inclusion into the the agenda of the Commission of Social and Employment Issues at the National Parliament, based on conclusions of the final report by expanded working group 2. Presentation during the Council of the State Secretaries on effective and economically for the State HIV treatment options, which allows to increase the number of people treated 3. The same presentation at Commission of Social and Employment Issues at the National Parliament | - July 1, Changes to Epidemiological Safety Law submitted in writting to Health Minister, so municipalities may establish harm reduction programmes on their territories by their own initiatives http://www.apvienibahiv.lv/index.php?p=8096&lang=886&a=2&b=1&lbu=5078 - July 22, The MoH accepted proposed changes to Epidemiological Safety Law and distributed them for discussions within stakeholders - September 4, Proposed concrete needed legislation changes to improve situation as guaranteed under Article 17 of Treatment Law, to receive health care services without any discrimination also being jailed http://www.apvienibahiv.lv/index.php?p=8096&lang=886&a=2&b=1&lbu=6678 | These are first steps and first concrete proposals in State Laws changes made by HIV/AIDS NGOs during past years with the goal to improve quality of life of PLWHA. Unfortunately Minister of Health Mr. D. Gavars will continue to work until new government in place after elections of the Parliament. This means us to be affraid from political instability. This minister is non-partisan, therefore he is not influenced by politicians. |
| F. Legislative documents adopted by the Parliament 1. Press release and press conference on results of the project 2. NGO's representatives participate at sitting of the Cabinet of Ministers, while viewing legislative changes 3. NGO's representatives participate at sittings of the Parliament commissions, while viewing legislative changes |  |  |
| G. Any other activities? | Please see factsheet table with all related activities in real time attached | There is a column "Lessons learned, problems" in the table |
| H. What are the impacts of your advocacy activities (April – September 2010)? | MoH became very opened to discussions because of high international authority of HIV/AIDS NGO-s. The common information about TMAP MTT8 activity since its beginning in December 2009 had very effective impact to increase the number of HIV/AIDS patients receiving ARV-s from month to month (439 on January 1, 2010 up to 511 on August 1, 2010). Publicity has good impact to improve situation (for example after press conference at May 14 The Riga Municipality Council found money to finance outreach work at Riga until the end of the year.) It is very important to have more documents / reports on situation in Latvia to improve this situation, so state's authorities regularly are "poking" (for example Shadow UNGASS Report includes the same problems with HIV treatment access and prophylaxis, as in MTT8 Report, among other related querries.) The new State Public Health coordination Commission established! This is exelent opportunity to work on the National Public Health Strategy for 2011 - 2017 (for example there is written in project that the State Program on prevention of tuberculosis must be developed and accepted.) Harm reduction definition and description are included into the State Drug Policy guidelines as separate chapter. |  |

Please indicate which of the following materials or tools you developed for your activity(ies)

| Protest picket Brochure in the state language Letters to officials Regular articles/information on the web-site | Media brief Meeting minutes for internal use Factsheet Official meetings minutes | Interview s in newspapers Media articles Alternative Report to UNGASS Proposals on legislation changes |
| --- | --- | --- |

Organisation's web-site as advocacy instrument: 
continous information in Latvian http://www.apvienibahiv.lv/index.php?p=8096&lang=886&gads=2010; 
in Russian http://www.apvienibahiv.lv/index.php?p=8097&lang=951&gads=2010; 
Project's documentation (see  fasting materials here)  http://www.apvienibahiv.lv/index.php?p=3350&lang=886; 
fasting news in English http://www.apvienibahiv.lv/index.php?p=8134&lang=1225
Official meetings minutes http://www.apvienibahiv.lv/index.php?p=9348&lang=886

Please note Please send copies of any campaign materials to Erika Baehr (erikabaehr@gmail.com) or provide us with the link to download. If the material is available only in hard copy, please send it to the following address;

ITPC Secretariat - 51/2, 3rd Floor Ruamrudee Building 3, Soi RuamRudee, Ploenchit Rd., Lumpini, Pathumwan, Bangkok 10330 THAILAND

Thank you very much for your time.

TMAP Secretariat – Aditi, Erika, and Ed