Project title:

Hepatitis C: hesitation is dangerous

Organisation:

Biedrība Apvieniba HIV.LV (Society Association HIV.LV)

Country:

Latvia

Grant Number 20031147

NARRATIVE  REPORT

1. Statement of purpose

To study real situation with Hepatitis C in Latvia, needs in treatment and treatment accessibility, and needs in advocacy. To develop recommendations for policy makers and stakeholders.

2. Project goals

| To study real situation with Hepatitis C in Latvia, needs in treatment and treatment accessibility, and needs in advocacy | Achieved Results published: http://www.apvienibahiv.lv/docs/729/projekti_2011/Report_HCV_LV2011_ENG.pdf |
| --- | --- |
| To receive reliable data on prevalence of Hepatitis C among prison inmates (DPs) and commercial sex-workers (CSWs) | Achieved Results published: DPs: http://www.apvienibahiv.lv/docs/729/projekti_2011/Testesanas_rezultati_cietumi.doc ; http://www.apvienibahiv.lv/docs/729/projekti_2011/Ieslodzito_aptauja_final.pdf CSWs: http://www.apvienibahiv.lv/docs/729/projekti_2011/KSD_Aptauja_HCV.pdf |
| To develop recommendations for policy makers and stakeholders | Achieved Results published: http://www.apvienibahiv.lv/docs/729/projekti_2011/Report_HCV_LV2011_ENG.pdf |
| To issue the first Report on the study on situation with HCV in Latvia and access to its treatment, made by non-governmental organisation | Achieved Results published: http://www.apvienibahiv.lv/docs/729/projekti_2011/HCV_Atskaite_broshura.pdf |
| To comprehend directions of the organisation in its future advocacy activities | Achieved Results published: http://www.apvienibahiv.lv/docs/729/2011-dazadi/AdvokacijasVirzieni2011_LAT.doc |

3. Project activities planned and implemented

| Planned activities (as listed at project proposal) | Number planned | Implementation level | Number achieved |
| --- | --- | --- | --- |
| Purchases and contracts with persons involved in the project | - | Fully | - |
| Agreement with Latvia's Prison Administration to work in prisons | - | Fully, published http://www.apvienibahiv.lv/docs/729/projekti_2011/vienoshanas_ar_IeVP.doc | - |
| Preparation of the guidelines and structure (template) of interviews with experts and of questionnaire for patients | - | Fully, published http://www.apvienibahiv.lv/docs/729/projekti_2011/eksp_interv_vadlinijas.doc ; http://www.apvienibahiv.lv/docs/729/projekti_2011/HCV_anketa_ieslodzitie.doc ; http://www.apvienibahiv.lv/docs/729/projekti_2011/HCV_anketa_sievietes.doc | - |
| Voluntary counceling and testing to hepatitis C and HIV in prisons by qualified nurse | 200 DPs / 20 sessions | Fully, exceeded | 208 DPs / 20 sessions |
| Peer-to-peer counceling while testing in prisons and interview of infected with HCV prisoners (questionnaire) | 200 DPs / 20 sessions | Fully, exceeded | 212 DPs / 20 sessions |
| Interviews with experts | 8 | Fully | 8 |
| Voluntary counceling and testing to hepatitis C in outreach work among commercial sex-workers by qualified nurse | 100 CSWs | Fully, exceeded | 120 CSWs |
| Survey with HCV-infected people | 100 respondents | Fully, exceeded | Total 169: 109 DPs 60 CSWs |
| Processing and consolidation of the material (surveys, interviews) obtained | 8 interviews 100 surveys | Fully, exceeded | 8 interviews 169 surveys |
| Report on the study on situation with HCV in Latvia and access to its treatment in place (in the Latvian language) | - | Fully, published http://www.apvienibahiv.lv/docs/729/projekti_2011/Report_HCV_LV2011_LAT.pdf | - |
| Report's translation into the English language and open for comment; Report in English finalized | - | Fully, published http://www.apvienibahiv.lv/docs/729/projekti_2011/Report_HCV_LV2011_ENG.pdf | - |
| Report's translation into the Russian language | - | Fully, published http://www.apvienibahiv.lv/docs/729/projekti_2011/Report_HCV_LV2011_RUS.pdf | - |
| Report's brochure layout preparing and sending to typography to print | 2 languages | Fully, exceeded, published http://www.apvienibahiv.lv/docs/729/projekti_2011/HCV_Atskaite_broshura.pdf | 3 languages |
| Brochure with Report on the study on situation with HCV in Latvia and access to its treatment in place (from typography) | 50 copies | Fully, exceeded | 200 copies |
| Presentation of the Report and its recommendations during the roundtable (Latvia's Infectology Centre, Health Economics Centre, Ministry of Health officials, NGO-s) at Latvia's Ministry of Health | - | Not implemented, but the project was presented at the meeting of MoH's Coordinative Commission of Limiting the Prevalence of HIV, TB and STD in March 16, 2011: Presentation published http://www.apvienibahiv.lv/docs/729/Komisiju_protokoli/prezentacija16032011.ppt Minutes published http://www.apvienibahiv.lv/docs/729/Komisiju_protokoli/HIVKKprot_nr14_160311.doc After extraordinary elections of the Parliament in September, 2011 the new Government will be formed at October, 2011, also new Minister of Health appointed. The Health Economics centre and some other institutions will be eliminated since November 1-st, 2011, and new National Health Service established. So, the future structure of health services in Latvia is unclear this time, because it is under discussions, also there is possible that the Ministry of Health itself will be eliminated after a new government approval. When things above become clear some activities of this project will be continued (see chapter 4 of this Report). | - |
| Identification of needs in advocacy on HCV treatment access | - | Fully in the Report | - |
| Project publicity at organisation's web-site www.apvienibahiv.lv | - | Constantly: actualities and project documentation | - |
| Project publicity at other media (press release in the beginning and in the end, articles at friendly web-sites and newspapers) | - | Not yet implemented. It is planned in the middle of November, 2011, when new Health institutions and | - |

4. Additional activities outside the project and activities after the project finished, and follow-up:

| Planned activities (as listed at project proposal) | Timeline (as indicated at project proposal) and implementation | Timeline of implementation |
| --- | --- | --- |
| Participating at Health Economics Centre's research on the spread of infectious diseases in prisons as expert from NGO | October, 2010 Implemented. Results presented at the meeting of MoH's Coordinative Commission of Limiting the Prevalence of HIV, TB and STD in May 18, 2011. Presentation published http://www.apvienibahiv.lv/docs/729/Komisiju_protokoli/cietumu_medicina.ppt Minutes published http://www.apvienibahiv.lv/docs/729/Komisiju_protokoli/KKprot_nr15_180511.doc | - |
| Participating in the International Round Table devoted to the topic of Hepatitis C, carried out in Ukraine, Donetsk (organized by OSI). Representative doctor from Latvia's Infectology Centre also is nominated | Late November or early December, 2010 Not implemented because of organizers (HEALTHUP, International Charitable Foundation, Ukraine) | Not known |
| Results of the Round Table discussed at Latvia's Infectology Centre | January, 2010 Not implemented – the reason see above. | Not known |
| Brochure with Report distributed within stakeholders and officials | Within a month after project finished | October, 2011 |
| Reporting to OSI (narrative and financial reports) | 20 days after project finished. Done with this. | - |
| Allies in advocacy identificated, and advocacy working group, including possible allies, established | Within 2 months after project finished. Partial implementation is done commonly with the society AGIHAS. Advocacy directions are confirmed in July, 2011 and published in Russian http://www.apvienibahiv.lv/docs/729/2011-dazadi/AdvokacijasVirzieni2011_RUS.doc ; in Latvian http://www.apvienibahiv.lv/docs/729/2011-dazadi/AdvokacijasVirzieni2011_LAT.doc | November 30, 2011 First meeting of the group December 1, 2011 |
| Short term (no longer than for 1 year) advocacy plan developed, potential funders identified | Within 3 months after project finished | December 31, 2011 |
| Advocacy plan published at organisation's web-site and at friendly web-sites and newspapers |  | January, 2012 |
| Report and its recommendations, needs in advocacy presented at sittings of the State Public Health Coordination Commission and State HIV Coordination Commission | Within 6 months after project finished | November 23, 2011 |
| If there will be funders to advocacy project identified, the project proposal submitted | while possible | While possible |

The Society „Association HIV.LV”:

- till January 31, 2012 should prepare follow-up report on this project

- in 2013 should prepare a report on the progress in the situation of hepatitis C and its treatment in Latvia.

All other reporting data please see at the "Report on the Hepatitis C and its Treatment Situation in Latvia", prepared by the Society “Association HIV.LV” as a result of this project.

Board Chair                                                                             Aleksandrs Molokovskis

September 25-th, 2011